## Recommendations Worksheet
Section | Report Page # | Rec Number | Recommendation Full Text | Workstream | SBAR | SBAR Status | Date SBAR Approved | SBAR Month Prepared | Start Date | Target Date | % Complete | Status | Notes
Tone from the Top | 42 | A | Affirm resolute commitments to diversity, equity, inclusion, and anti-racism.
Tone from the Top | 42 | A1 | Develop ambitious, concrete, and measurable plans for organizing and operationalizing commitments to DEI and anti-racism guided by these findings and recommendations. Dr. Jacobs, the Board of Directors, and the executive leadership team should communicate these plans to the OHSU community, including implementation timelines and mechanisms for holding designated leaders accountable and should provide periodic progress updates. | Vision, Strategy, and Change | Develop and Communicate a Strategic DEIB-Vision for the Organization | Deferred | NA | July
|  |  |  | Vision, Strategy, and Change | Operationalize Commitments to DEIB | Deferred | NA | December
Tone from the Top | 42 | A2 | Continue to conduct employee engagement surveys and to include DEI-focused questions; continue to monitor trends in employee engagement and disaggregate the data by select demographics such as race, gender, and tenure; and have Dr. Jacobs, the Board of Directors or the executive leadership team report to the OHSU community on trends and efforts to address them. | Vision, Strategy, and Change | Continue to Conduct Regular Employee Engagement Surveys | Approved | 2023-06-01 | June | 2023-01-01 | 2024-07-01 | 85% | Green | The Employee Engagement Survey has closed. Next steps are to analyze the feedback, communicate the results, and develop Action Plans to address the findings.
Tone from the Top | 42 | A3 | Consider a schedule of regular meetings between the executive leadership team, CDI leadership, and all relevant affinity groups to identify and discuss issues related to DEI and anti-racism. Ensure that these meetings incorporate a formal mechanism for members of inclusion networks to communicate feedback to the executive leadership team. | Clarify / Elevate the Role of CDI | CDI Collaboration with DEIB-Focused Functions | Deferred | NA | July
Tone from the Top | 42 | B | Elevate diversity, equity, and inclusion throughout the institution by fully and cohesively incorporating these concepts into OHSU’s policies, practices, and culture.
Tone from the Top | 42 | B1 | Develop a strategic institution-wide DEI vision with actionable, meaningful, and prioritized initiatives to be led by CDI. | Vision, Strategy, and Change | Develop and Communicate a Strategic DEIB-Vision for the Organization | Deferred | NA | July
|  |  |  | Vision, Strategy, and Change | Operationalize Commitments to DEIB | Deferred | NA | December
|  |  |  | Clarify / Elevate the Role of CDI | Clearly Define and Communicate the Roles and Responsibilities for CDI at OHSU | Submitted to Implementation Committee - Rnd 3+ | NA | June
Tone from the Top | 43 | B2 | Ensure effective collaboration between CDI and all DEI-focused functions, groups, and roles across the various missions, including periodic meetings with the head of CDI to ensure actions are aligned with the institution-wide DEI vision. | Clarify / Elevate the Role of CDI | CDI Collaboration with DEIB-Focused Functions | Deferred | NA | July
Tone from the Top | 43 | B3 | Address DEI with similar detail and clarity across the Code of Conduct, Discrimination and Harassment Policy, and Reporting Policy. | Re-Engineer Incident Processes (Policies and Definitions) | Update the Code of Conduct | Submitted to Implementation Committee - Rnd 2 | NA | November | 2022-05-15 | TBD | 75% | Green | The Discrimination, Harassment and Retaliation (DHR) policy has been reviewed by the Oversight Committee, the Policy Advisory Committee, and the OHSU community at large. The policy has been signed by Dr. Jacobs and is live. The DHR Policy also addresses reporting requirements. The first draft of the Update the Code of Conduct SBAR is under review by the Oversight Committee.
|  |  |  | Re-Engineer Incident Processes (Policies and Definitions) | Update the Discrimination, Harassment, and Retaliation Policy | Approved | 2022-12-01 | June
|  |  |  | Re-Engineer Incident Processes (Policies and Definitions) | Update the Reporting Policy | Deferred | NA | September
Tone from the Top | 43 | B4 | Increase the diversity of OHSU’s workforce by (1) assessing OHSU’s requirements to hire internal candidates; (2) encouraging leaders to increase the percentage of diverse candidates in the pipeline for leadership positions and holding them accountable for improvements including by considering external candidates; and (3) considering requirements concerning the diversity of applicant slates for senior positions with a goal of increasing the percentage of diverse applicants year-over-year. | Increase Workforce Diversity | NA - This Recommendation is Complete | Approved | NA | March | 2022-03-01 | TBD | 30% | Green | The SBAR related to assessing OHSU’s requirements to hire internal candidates was submitted to and approved by the Position Management Committee, prior to implementation of the SBAR process for the Covington response work. OHSU is now once again considering external candidates for positions. Work on developing DEIB-related objectives for managers and increasing the diversity of candidate pools for leadership positions will start after the associated SBARs are approved. First drafts of both SBARs have been reviewed by the Implementation Committee.
|  |  |  | Increase Workforce Diversity | Increase the Diversity of Candidate Pools for Leadership Positions | Submitted to Implementation Committee - Rnd 1 | NA | December
|  |  |  | Develop Objectives for Managers | Develop DEIB Related Objectives for Managers | Submitted to Oversight Committee - Rnd 1 | NA | November
Tone from the Top | 43 | B5 | Evaluate contributions to OHSU’s culture and DEI commitment in the performance review process for all managers, deans, department chairs, and EVPs across the institution, further encouraging diversification of the workforce and improving retention of diverse employees over a specified number of years. | Develop Objectives for Managers | Develop DEIB Related Objectives for Managers | Submitted to Oversight Committee - Rnd 1 | NA | November
Tone from the Top | 43 | B6 | Adopt a system to consistently track diversity metrics in hiring, performance evaluations, promotion, compensation, discipline, retention, and attrition. Implement a process to regularly review these metrics and take action to identify and improve disparities. | Report on Metrics | Report on HR Metrics | Submitted to Oversight Committee - Rnd 2 | NA | November
Tone from the Top | 43 | B7 | Respond to nationwide and internal events implicating inequity with clear, consistent, and timely communications | Vision, Strategy, and Change | Respond to Nationwide and Internal Events | Approved | 2023-04-15 | August | 2022-07-15 | 2023-04-01 | 100% | Complete | The Public Stance Position memo and process are now final. The effectiveness of the approach will be monitored through formal reviews after new communications are drafted and deployed.
Tone from the Top | 43 | B8 | Develop and conduct additional community-wide trainings on DEI-related issues, in addition to unconscious bias training. Develop targeted trainings focused on DEI principles for HR, AAEO, Integrity, and managers/supervisors. | Clarify / Elevate the Role of CDI | Develop and Conduct Additional DEIB-Related Trainings | Submitted to Implementation Committee - Rnd 1 | NA | November
Tone from the Top | 43 | C | Strengthen accountability and ensure that all OHSU community members understand the importance of meeting the institution’s expectations regarding conduct and culture.
Tone from the Top | 43 | C1 | Dr. Jacobs and the executive leadership team should communicate widely and often that any individual found to have engaged in misconduct will be held accountable, no matter what position they hold at OHSU | Re-Engineer Incident Processes (Discipline) | Communicate the Proposed Disciplinary Guidelines | Approved | 2022-12-01 | June | 2022-05-15 | TBD | 50% | Green | The Discipline Guidelines are complete. In addition, the project team has developed a first draft communications and training plan for the rollout of the new Covington policies and the related Discipline Guidelines. This draft has been reviewed by the Implementation Committee and will be submitted to the Oversight Committee for review.
Tone from the Top | 43 | C2 | Appropriately revise and finalize the proposed Disciplinary Matrix to ensure consistent consequences for engaging in misconduct. Make clear that HR’s disciplinary recommendations, in consultation with stakeholders, are presumptively followed by managers across the missions, including the School of Medicine, and remove managerial discretion to override HR’s recommendation without approval from an independent body or advisory board, comprised of various stakeholders, assigned to resolve these disagreements. | Re-Engineer Incident Processes (Discipline) | Communicate the Proposed Disciplinary Guidelines | Approved | 2022-12-01 | June | 2022-05-15 | TBD | 50% | Green | The Discipline Guidelines are complete. In addition, the project team has developed a first draft communications and training plan for the rollout of the new Covington policies and the related Discipline Guidelines. This draft has been reviewed by the Implementation Committee.
Tone from the Top | 43-44 | C3 | Inform the OHSU community about the Disciplinary Matrix and reinforce that it is intended to ensure consistent disciplinary outcomes regardless of status within the institution or protected characteristics. Clarify how certain behaviors, including microaggressions or other disrespectful conduct, will be treated under the Disciplinary Matrix. | Re-Engineer Incident Processes (Discipline) | Communicate the Proposed Disciplinary Guidelines | Approved | 2022-12-01 | June | 2022-05-15 | TBD | 50% | Green | The Discipline Guidelines are complete. In addition, the project team has developed a first draft communications and training plan for the rollout of the new Covington policies and the related Discipline Guidelines. This draft has been reviewed by the Implementation Committee.
Tone from the Top | 44 | C4 | Consider establishing an advisory board, comprised of representatives from HR, AAEO, Legal, and CDI, to periodically review and make recommendations for revisions to the Disciplinary Matrix. | Re-Engineer Incident Processes (Discipline) | Communicate the Proposed Disciplinary Guidelines | Approved | 2022-12-01 | June
Tone from the Top | 44 | C5 | Adopt guidance and processes applicable to all missions, including the School of Medicine, regarding communications for departing employees who have engaged in conduct that violates OHSU policies. | Re-Engineer Incident Processes (Discipline) | Communicate the Proposed Disciplinary Guidelines | Approved | 2022-12-01 | June | 2022-05-15 | TBD | 50% | Green | The Discipline Guidelines are complete. In addition, the project team has developed a first draft communications and training plan for the rollout of the new Covington policies and the related Discipline Guidelines. This draft has been reviewed by the Implementation Committee.
Resources and Staffing | 44 | A | Conduct a rigorous, competitive, and nationwide search for a highly qualified candidate for a VP or SVP of HR, with relevant and sustained leadership experience, and ensure that this individual acts as a strategic partner to the executive leadership team, bringing professionalism to the HR function and supporting achievement of OHSU’s DEI goals and objectives. | Improve the Effectiveness of the People Function | NA - The EVP of People position description served as the pilot feedback process. The search for a new EVP of People is underway. | NA | NA | NA | 2022-03-01 | 2022-09-30 | 100% | Complete | Qiana Williams joined OHSU as our first Executive Vice President and Chief People Officer on Oct. 17, 2022.
Resources and Staffing | 44 | B | Centralize HR functions so that all HR professionals across the institution ultimately report up to the VP (or SVP) of HR. | Improve the Effectiveness of the People Function | Centralize HR Staff and Functions | Submitted to Implementation Committee - Rnd 3+ | NA | July
Resources and Staffing | 44 | C | Provide HR and AAEO personnel who conduct investigations sophisticated mandatory training on investigative procedures, including Title IX procedures. | Improve the Effectiveness of the People Function | Provide Sophisticated Training to HR Investigators | Submitted to Implementation Committee - Rnd 2 | NA | August
|  |  |  | Realign the AAEO | Provide Sophisticated Training to AAEO Investigators | Submitted to Implementation Committee - Rnd 3+ | NA | October
Resources and Staffing | 44 | D | Restructure, increase, and diversify staffing in HR and AAEO
Resources and Staffing | 44 | D1 | Establish AAEO as a separate, neutral, independent investigative and compliance function with responsibility for investigation of conduct that potentially violates Title VII or Title IX. To maintain its independence and neutrality, and ensure accessibility to students, separate AAEO from HR or CDI, which have fundamentally different objectives and goals. Instead, we recommend that AAEO report to Integrity, itself a compliance function, which reports to OHSU Legal. AAEO should report the outcomes of its investigations to HR, which, as explained above, would be tasked with making a disciplinary recommendation in accordance with the Disciplinary Matrix. | Realign the AAEO | Realign the AAEO | Approved | 2022-07-15 | May | 2022-07-16 | 2022-07-30 | 100% | Complete | The Affirmative Action and Equal Opportunity (AAEO) Director position is now reporting into Tim Marshall, the OHSU Chief Integrity Officer, and fiscal authority has also been realigned to ensure that budgets match reporting structures. Finally, the name of the AAEO has been changed to the Office of Civil Rights Investigations and Compliance (OCIC).
Resources and Staffing | 44 | D2 | Develop a multi-year plan to increase the number of HRBPs so that individual HRBPs are responsible for fewer employees. When hiring these HRBPs, focus on increasing the diversity of HRBPs. | Improve the Effectiveness of the People Function | Increase the Number and Diversity of HR Business Partners | Submitted to Implementation Committee - Rnd 2 | NA | October
Resources and Staffing | 44 | D3 | Increase the number of AAEO investigators to support recent caseload increases. When hiring these investigators, focus on increasing the diversity of AAEO investigators. | Realign the AAEO | Increase the Number and Diversity of AAEO Investigators | Approved | 2023-04-15 | July | 2023-04-01 | 2023-10-01 | 25% | Green | The SBAR identifies five new positions that will be hired by the OCIC - AVP / Title IX Coordinator, Deputy Director, Intake Specialist, Investigator/Trainer, and Intake Specialist/Training Coordinator. The AVP/Title IX Coordinator has been hired. Recruiting is underway for the Intake Specialist. The remaining three positions will be filled during FY24. Following these hires, the OCIC will have 6 Investigators on staff, with additional Investigators provided by third party consultants, as needed, based on the number of incidents at any given time. The OCIC is attempting to increase the diversity of the candidate pools by posting positions more broadly, including with Partners in Diversity, LinkedIn, and the Oregon State Bar Association. OCIC members are also leveraging LinkedIn to reach out directly to qualified candidates.
Resources and Staffing | 44 | D4 | To reduce and focus the workload of AAEO investigators, consider transferring, with an appropriate transition and training plan, the handling of ADA employee accommodation requests from AAEO to HR (for the full lifecycle of a request through implementation of the accommodation). HR should consult Legal when questions arise in assessing or implementing accommodations. The current ADA Coordinator could be transferred from AAEO to HR to facilitate this change and help train others in HR to assess and implement accommodation requests. | Realign the AAEO | Transfer Responsibility for Accommodations from the AAEO to HR | Approved | 2023-06-23 | August | 2023-06-01 | 2023-10-01 | 50% | Green | OHSU is currently implementing a new Office of Employee Accommodations within the HR function. HR is currently in the process of posting new positions and hiring staff.
Policies and Procedures | 45 | A | Clearly define prohibited conduct throughout OHSU’s policies and explain how the institution addresses such misconduct.
Policies and Procedures | 45 | A1 | Provide clear definitions of all forms of prohibited conduct so that OHSU community members understand and can identify it. Specific examples of discrimination, harassment, and retaliation should be added to relevant policies as needed. Fully explain the details regarding how such misconduct (1) should be reported and (2) will be handled | Re-Engineer Incident Processes (Policies and Definitions) | Update the Code of Conduct | Submitted to Implementation Committee - Rnd 2 | NA | November | 2022-05-15 | TBD | 60% | Green | The DHR policy has been reviewed by the Oversight Committee, the Policy Advisory Committee, and the OHSU community at large. The policy has been signed by Dr. Jacobs and is live. The Bullying Policy has been approved by the Oversight Committee and submitted to the Policy Advisory Committee. The first draft of the Update the Code of Conduct SBAR is under review by the Oversight Committee. In addition, the project team has developed a first draft communications and training plan for the rollout of the new Covington policies and the related Discipline Guidelines. This draft has been reviewed by the Implementation Committee. Finally, updates to reporting channels will be defined and implemented as part of the project to implement a Centralized Case Management and Reporting System.
|  |  |  | Re-Engineer Incident Processes (Policies and Definitions) | Update the Discrimination, Harassment, and Retaliation Policy | Approved | 2022-12-01 | June
|  |  |  | Re-Engineer Incident Processes (Policies and Definitions) | Update the Reporting Policy | Deferred | NA | September
|  |  |  | Re-Engineer Incident Processes (Reporting Channels) | Reduce the Complexity of Reporting Channels | Submitted to Implementation Committee - Rnd 3+ | NA | September
Policies and Procedures | 45 | A2 | Provide additional information on the concepts of “microaggressions,” “mis gendering,” and “racism” that were recently added to these policies, which explains how those concepts may materialize as discrimination and harassment and the consequences for engaging in those actions. | Re-Engineer Incident Processes (Policies and Definitions) | Update the Code of Conduct | Submitted to Implementation Committee - Rnd 2 | NA | November | 2022-05-15 | TBD | 75% | Green | The DHR policy has been reviewed by the Oversight Committee, the Policy Advisory Committee, and the OHSU community at large. The policy has been signed by Dr. Jacobs and is live. Reporting requirements are defined in the DHR Policy. The first draft of the Update the Code of Conduct SBAR has been reviewed by the Oversight Committee.
|  |  |  | Re-Engineer Incident Processes (Policies and Definitions) | Update the Discrimination, Harassment, and Retaliation Policy | Approved | 2022-12-01 | June
|  |  |  | Re-Engineer Incident Processes (Policies and Definitions) | Update the Reporting Policy | Deferred | NA | September
Policies and Procedures | 45 | A3 | Decide whether to add concepts such as “bullying” to relevant policies or reduce and define such concepts into a single category such as “disrespectful treatment." | Re-Engineer Incident Processes (Policies and Definitions) | Update the Code of Conduct | Submitted to Implementation Committee - Rnd 2 | NA | November | 2022-05-15 | TBD | 75% | Green | The DHR policy has been reviewed by the Oversight Committee, the Policy Advisory Committee, and the OHSU community at large. The policy has been signed by Dr. Jacobs and is live. Reporting requirements are defined in the DHR Policy. The first draft of the Update the Code of Conduct SBAR has been reviewed by the Oversight Committee.
|  |  |  | Re-Engineer Incident Processes (Policies and Definitions) | Update the Discrimination, Harassment, and Retaliation Policy | Approved | 2022-12-01 | June
|  |  |  | Re-Engineer Incident Processes (Policies and Definitions) | Update the Bullying Policy | Approved | 2023-04-01 | August
Policies and Procedures | 45 | B | Revise and streamline reporting and investigation procedures to ensure more clear and consistent processes for reporting parties, mandatory reporters, and investigators.
Policies and Procedures | 45 | B1 | Revise the complaint reporting and investigation procedures so that OHSU members understand how to report issues and mandatory reporters understand the type of issues that need to be elevated and their obligations to elevate them. Ensure that all policies and publications that explain these procedures, including resources available on the AAEO page of OHSU’s website, are internally consistent and consistent with each other. | Re-Engineer Incident Processes (Reporting Channels) | Reduce the Complexity of Reporting Channels | Submitted to Implementation Committee - Rnd 3+ | NA | September | 2022-08-15 | TBD | 50% | Green | Reporting requirements have been incorporated into the DHR Policy which has been finalized and signed by Dr. Jacobs. Updates to reporting channels will be defined and implemented as part of the project to implement a Centralized Case Management and Reporting System.
|  |  |  | Re-Engineer Incident Processes (Mandatory Reporting) | Update the Reporting Policy | Deferred | NA | September
Policies and Procedures | 45 | B2 | Promulgate clearer guidance concerning which investigations are to be conducted by AAEO and which are to be conducted by HR, as well as guidelines for when other departments, such as Legal, should be consulted in connection with investigations. | Re-Engineer Incident Processes (Investigations) | Develop and Communicate a Standardized, Comprehensive Investigations Policy | Submitted to Oversight Committee - Rnd 2 | NA | September | 2022-08-15 | TBD | 50% | Green | The second draft of the Investigations Policy is ready for review by the Oversight Committee.
Policies and Procedures | 45 | B3 | Adopt a single investigations policy for all investigations into misconduct relevant to this assessment and ensure that policies thoroughly address all aspects of investigations. This policy would be utilized by both AAEO and HR, as well as any other department that conducts investigations. | Re-Engineer Incident Processes (Investigations) | Develop and Communicate a Standardized, Comprehensive Investigations Policy | Submitted to Oversight Committee - Rnd 2 | NA | September | 2022-08-15 | TBD | 50% | Green | The second draft of the Investigations Policy is ready for review by the Oversight Committee.
Policies and Procedures | 45 | B4 | Describe the reporting and investigation process clearly in the Reporting Policy as well as in a resource available on the AAEO page of OHSU’s website so that community members understand what happens when a report is made. | Re-Engineer Incident Processes (Policies and Definitions) | Update the Reporting Policy | Deferred | NA | September | 2022-08-15 | TBD | 50% | Green | The second draft of the Investigations Policy is ready for review by the Oversight Committee. Reporting requirements have been incorporated into the DHR Policy which has been finalized and signed by Dr. Jacobs. Updates to reporting channels will be defined and implemented as part of the project to implement a Centralized Case Management and Reporting System.
|  |  |  | Re-Engineer Incident Processes (Reporting Channels) | Develop and Communicate a Standardized, Comprehensive Investigations Policy | Submitted to Oversight Committee - Rnd 2 | NA | September
Policies and Procedures | 45 | B5 | Require investigators to explain to reporters at the beginning of the investigation process that investigators may not be able to disclose any resulting discipline due to confidentiality concerns. Public-facing policies related to reporting and investigations should explain this limitation. | Re-Engineer Incident Processes (Investigations) | Develop and Communicate a Standardized, Comprehensive Investigations Policy | Submitted to Oversight Committee - Rnd 2 | NA | September | 2022-08-15 | TBD | 50% | Green | The second draft of the Investigations Policy is ready for review by the Oversight Committee.
Policies and Procedures | 46 | B6 | Require investigators to consistently notify affected parties about the status of complaints. Standardize close-out procedures, including how and when an outcome is communicated to affected parties. | Re-Engineer Incident Processes (Investigations) | Develop and Communicate a Standardized, Comprehensive Investigations Policy | Submitted to Oversight Committee - Rnd 2 | NA | September | 2022-08-15 | TBD | 50% | Green | The second draft of the Investigations Policy is ready for review by the Oversight Committee.
Policies and Procedures | 46 | B7 | Disclose to the community de-identified and aggregated data about complaints involving misconduct during a given reporting period, including the volume of different categories of complaints, the types of resolutions reached, and how long they took to resolve. | Report on Metrics | Consolidated Data Repository and Centralized Reporting System | Approved | 2022-07-15 | May | 2022-07-16 | 2023-07-31 | 60% | Green | Navex, the EthicsPoint vendor, has delivered a first iteration of the baseline Centralized Incident Management and Reporting System. The project team is currently testing the delivered application.
Policies and Procedures | 46 | C | Streamline the channels listed in policies and guidance documents related to reporting.
Policies and Procedures | 46 | C1 | Consider designating the Integrity Ethics Point Hotline as the central channel for receiving all reports made under OHSU policies rather than suggesting different reporting channels for Title IX and non-Title IX matters. Consider reducing the overall number of reporting channels. All other reporting channels should be listed as alternative options to the Integrity Ethics Point Hotline, and all recipients of complaints made through those other channels should be trained either to make or transfer the report to the Integrity Ethics Point Hotline for triage, tracking, and follow-up so that all complaints across the institution, no matter which channel they come through, are funneled into one system. Ensure that guidance clarifies how to appropriately direct reports to relevant teams for follow-up and investigation. | Re-Engineer Incident Processes (Reporting Channels) | Consolidated Data Repository and Centralized Reporting System | Approved | 2022-07-15 | May | 2022-07-16 | 2023-07-31 | 60% | Green | Navex, the EthicsPoint vendor, has delivered a first iteration of the baseline Centralized Incident Management and Reporting System. The project team is currently testing the delivered application.
Policies and Procedures | 46 | C2 | Develop a standardized and consistent approach to complaint and investigations recordkeeping. Rather than adopting a third tracking or triage system for HR, maintain all complaints in Integrity’s Ethics Point database, and grant relevant AAEO and HR personnel full access to records for personnel they are investigating. Continue to provide reporters with the ability to periodically check on the status of their reports. | Re-Engineer Incident Processes (Investigations) | Consolidated Data Repository and Centralized Reporting System | Approved | 2022-07-15 | May | 2022-07-16 | 2023-07-31 | 60% | Green | Navex, the EthicsPoint vendor, has delivered a first iteration of the baseline Centralized Incident Management and Reporting System. The project team is currently testing the delivered application.
Policies and Procedures | 46 | C3 | Ensure that reporting channels are described consistently throughout policies and in communications to the community, including on websites, in flyers, brochures, and posters on reporting. | Re-Engineer Incident Processes (Reporting Channels) | Update the Reporting Policy | Deferred | NA | September | 2022-09-15 | TBD | 50% | Green | Reporting requirements have been defined in the revised DHR Policy which has been approved and signed by Dr. Jacobs.
Policies and Procedures | 46 | D | Strengthen mandatory reporter provisions in all relevant policies.
Policies and Procedures | 46 | D1 | Clearly describe the mandatory reporter obligation in the Reporting Policy, the Discrimination and Harassment Policy, and the Respect for All Guidebook and related flyers, and remove any language that suggests or implies that only supervisors “most directly involved” are mandatory reporters. | Re-Engineer Incident Processes (Mandatory Reporting) | Update the Reporting Policy | Deferred | NA | September | 2022-08-15 | TBD | 50% | Green | Reporting requirements have been defined in the revised DHR Policy which has been approved and signed by Dr. Jacobs.
Policies and Procedures | 46 | D2 | Add a provision on mandatory reporting obligations in the section of the Code of Conduct relating to supervisor obligations. | Re-Engineer Incident Processes (Mandatory Reporting) | Update the Code of Conduct | Submitted to Implementation Committee - Rnd 2 | NA | November
Policies and Procedures | 46 | D3 | Review other OHSU policies and procedures relating to discrimination and harassment, including proposed policies, and ensure that mandatory reporting obligations are addressed when appropriate. | Re-Engineer Incident Processes (Mandatory Reporting) | Update the Discrimination, Harassment, and Retaliation Policy | Approved | 2022-12-01 | June | 2022-05-15 | 2023-04-30 | 100% | Complete | Reporting requirements have been defined in the revised DHR Policy which has been approved and signed by Dr. Jacobs.
Policies and Procedures | 47 | E | Incorporate strong non-retaliation provisions throughout OHSU’s policies, and communicate broadly the institution’s prohibition on retaliation.
Policies and Procedures | 47 | E1 | Ensure that references to OHSU’s prohibition on retaliation are clear, robust, include examples, and are highlighted in any policy touching on reporting or misconduct | Re-Engineer Incident Processes (Non-Retaliation) | Update the Discrimination, Harassment, and Retaliation Policy | Approved | 2022-12-01 | June | 2022-05-15 | 2023-04-30 | 100% | Complete | The DHR policy has been reviewed by the Oversight Committee, the Policy Advisory Committee, and the OHSU community at large. The policy has been signed by Dr. Jacobs and is live.
Policies and Procedures | 47 | E2 | Modify provisions of other policies that may inhibit reporting. For example, in the Code of Conduct, OHSU should clarify that good faith complaints will be taken seriously even if the underlying conduct is not found to violate the law or OHSU policy, and the Guidebook should make clear that the concept of “free speech” cannot be used as a shield for engaging in prohibited misconduct. | Re-Engineer Incident Processes (Non-Retaliation) | Update the Code of Conduct | Submitted to Implementation Committee - Rnd 2 | NA | November
Policies and Procedures | 47 | E3 | Implement system for monitoring potential retaliation against complainants, including potentially the following:
Policies and Procedures | 47 | E3a | Investigators should check with complaining parties whose complaints they investigated at regular intervals (e.g., three months, six months, one year) following the complaint to determine if there are any potential retaliation concerns or issues | Re-Engineer Incident Processes (Non-Retaliation) | Implement Procedures to Monitor for Potential Retaliation | Submitted to Implementation Committee - Rnd 2 | NA | December
Policies and Procedures | 47 | E3b | In appropriate circumstances and with complainant consent, investigators should consider informing the complainant’s supervisor about the issue reported (unless it involves the supervisor) and ask the supervisor to monitor for potential retaliation | Re-Engineer Incident Processes (Non-Retaliation) | Implement Procedures to Monitor for Potential Retaliation | Submitted to Implementation Committee - Rnd 2 | NA | December
Policies and Procedures | 47 | E4 | Analyze attrition and promotion data to identify potential trends affecting individuals over time who make complaints or participate in investigations. | Re-Engineer Incident Processes (Non-Retaliation) | Implement Procedures to Monitor for Potential Retaliation | Submitted to Implementation Committee - Rnd 2 | NA | December

## Data Validation (hidden)
NA
Not Started
In Process
Submitted to Implementation Committee - Rnd 1
Submitted to Oversight Committee - Rnd 1
Submitted to Implementation Committee - Rnd 2
Submitted to Oversight Committee - Rnd 2
Submitted to Implementation Committee - Rnd 3+
Submitted to Oversight Committee - Rnd 3+
Approved
Deferred